## Load Projects
Queue Number | Developer Name | Project: Project Name | IR Submission Date | Peak MW load | End-Use | Record Type Name | Type/Fuel | County | State | NYISO Zone | Points of Interconnection | CTO/Utility | Affected Transmission Owner (ATO) | Project Status # | SIS Bundle | Last Updated Date | Availability of Studies | IA Tender Date | FS Completion Date | Proposed Initial Backfeed Date
205 | National Grid | Luther Forest | 2005-11-02 | 40 |  | Load Interconnection | L | Saratoga | NY | F | Round Lake 115kV | NM-NG |  | 14 |  | 2013-03-31 | SIS |  |  | I/S
849 | Somerset Operating Company, LLC | Somerset Load | 2019-05-21 | 250 |  | Load Interconnection | L | Niagara | NY | A | Kintigh 345kV | NYSEG |  | 14 |  | 2022-07-31 | SIS, FS |  |  | I/S
1446 | Air Products and Chemicals Inc | Massena Green Hydrogen | 2022-10-05 | 110 |  | Load Interconnection | L | St Lawrence | NY | E | Haverstock - Adirondack 345 kV line 1 | NYPA |  | 0 |  | 2025-03-31
1465 | Digihost Technologies, Inc. | Digihost load | 2022-11-14 | 50.2 |  | Load Interconnection | L | Niagara | NY | A | Walck Rd. 115kV | NM-NG |  | 14 |  | 1900-01-13 | N/A |  |  | I/S
0290A | Green Island Power Authority | Green Island Power | 2008-04-07 | 20 |  | Load Interconnection | L | Albany | NY | F | Maplewood - Johnson Rd 115kV | NM-NG |  | 14 |  | 2011-11-30 | SIS |  |  | I/S
0311 | NY State Electric & Gas | Concord Casino | 2008-09-24 | 48 |  | Load Interconnection | L | Sullivan | NY | E | Coopers Corner - Rock Hill | NYSEG |  | 0 |  | 2013-04-30
0580 | Genesee County Economic Devel. | WNY STAMP | 2016-09-27 | 300 | DAT | Load Interconnection | L | Genesee | NY | B | Kintigh/Niagara - New Rochester 345kV | NYPA |  | 12 | N/A | 2025-03-31 | SIS |  |  | 11-2026
0776 | Greenidge Generation LLC | Greenidge Load | 2018-10-22 | 60 | DAT-CM | Load Interconnection | L | Yates | NY | C | Greenidge 115kV | NYSEG |  | 7 | N/A | 2026-03-31 | SIS |  |  | 04-2030
0979 | North Country Data Center | North Country Data Center | 2020-01-22 | 435 | DAT-CM | Load Interconnection | L | St. Lawrence | NY | D | Reynolds 115kV | NYPA |  | 12 | N/A | 2026-07-31 | SIS |  |  | 01-2026
1315 | Sabey Data Center Properties, LLC | SDC St. Lawrence | 2021-12-20 | 120 | DAT | Load Interconnection | L | St. Lawrence | NY | D | Moses-Reynolds MRG-1 and Moses-Reynolds MRG-2 at 115kV | NYPA |  | 8 | N/A | 2026-07-31 | SIS |  |  | 11-2026
1536 | Micron New York Semiconductor Manufacturing LLC | White Pine Phase 1 | 2023-03-11 | 480 | M-CH | Load Interconnection | L | Onondaga | NY | C | Clay 345 kV Substation | NM-NG |  | 12 | N/A | 2025-04-30 | SIS |  |  | 06-2025
1713 | Project Sycamore - Orangeburg | Project Sycamore Orangeburg | 2024-06-19 | 22.3 | DAT | Load Interconnection | L | Rockland | NY | G | Oak Street 138kV | O&R |  | 10 | 25-1 | 2025-12-31 | SIS |  |  | 10-2029
1721 | WF Industrial XII LLC | Brookhaven Logistics Center | 2024-10-28 | 176.6 | DAT | Load Interconnection | L | Suffolk | NY | K | 138-872 Holbrook to Sills Rd | LIPA |  | 9 | N/A | 2025-12-31 | SIS |  |  | 12-2027
1730 | Arconic Corporation | Arsenal Data Site 1000 | 2025-03-07 | 467 | DAT-AI | Load Interconnection | L | St Lawrence | NY | E | Haverstock to Adirondak 345kV line HA-1 | NYPA | National Grid | 5 | 25-2 | 2026-06-30 |  |  |  | 05-2027
1738 | Donovan Drive Holdings LLC | 1 Gig Data Center East Fishkill, NY | 2025-07-17 | 1000 | DAT | Load Interconnection | L | Dutchess | NY | H | East Fishkill to Wood Street 345 kV lines (38 and 39) | CONED | NYSEG, Central Hudson | 5 | 26-2 | 2026-06-30 |  |  |  | 10-2026
1742 | St. Lawrence Infrastructure, LLC | St. Lawrence Infrastructure 1 | 2025-09-02 | 860 | DAT-AI | Load Interconnection | L | St. Lawrence | NY | E | NYPA HA-2, 345kV Transmission Line | NYPA |  | 4 | 26-4 | 2026-05-31 |  |  |  | 01-2030
1743 | St. Lawrence Infrastructure, LLC | St. Lawrence Infrastructure 2 | 2025-09-02 | 1935 | DAT-AI | Load Interconnection | L | St. Lawrence | NY | D | NYPA's 230kV Moses Massena 1 (MMS-1) and 230kV Moses Massena 2 (MMS-2) | NYPA |  | 4 | 26-4 | 2026-01-31 |  |  |  | 12-2028
1752 | The Agency | Broome County Tech Park | 2025-10-30 | 250 | RD | Load Interconnection | L | Broome | NY | C | 345 kV POI via a loop on the existing Oakdale-Fraser Line 32. The interconnection substation will have a ring bus configuration. | NYSEG | NGRID, NYPA | 5 | 26-3 | 2026-09-30 |  |  |  | 07-2037
1762 | Highwall Energy, LLC | Highwall Data Center | 2026-05-12 | 400 | DAT | Load Interconnection | L | Clearfield | PA | C | same POI of Q#1080 (Mineral Basin Solar), connects to NYSEG's L47 line | NYSEG |  | 4 |  | 2026-06-30 |  |  |  | 03-2029
1764 | Titan Mining Corporation | Kilbourne Graphite Concentrator Plant | 2026-07-16 | 15 |  | Load Interconnection | L | ST LAWRENCE | NY | E | ZINCO 115 | National Grid |  | 1 |  | 2026-07-31 |  |  |  | 03-2027
End-Use Key
DAT Data Center
AI AI Data center
CM Cryptocurrency mining data center
M Manufacturing
CH Microchip fabrication
CG Consumable Goods
IN Industrial Goods
RD Research and Development
HP Hydrogen Production
O Other
NOTES:
● Project status # Key:0=Withdrawn, 1=Scoping Meeting Pending, 2=FES Pending, 3=FES in Progress,3A=FES Approved/Performed, 4=SRIS/SIS Pending, 5=SRIS/SIS in Progress, 5P=SRIS Commenced, Stopped and Pending Adoption of IP, 6=SRIS/SIS Approved, 7=FS Pending, 8=Rejected Cost Allocation/Next FS Pending, 9=FS in Progress, 10=Accepted Cost Allocation/IA in Progress,
11=IA Completed, 12=Under Construction, 13=In Service for Test, 14=In Service Commercial, 0=Withdrawn, 15=Partial In-Service, P=Pending Adoption of IP Compliance with Order 2023
● Availability of Studies Key: None=Not Available, FES=Feasibility Study Available, SRIS=System Reliability Impact Study Available, FS=Facilities Study and/or ATRA Available
● Proposed In-Service Dates, Proposed Initial Synchronization Dates and Commercial Operation Dates (COD) are shown in format Year/Qualifier, where Qualifier may indicate the month, season, or quarter.
● The column labeled "SIS Bundle" refers to the groupings of load projects being studied in the same post project SIS case (bundle), as described in the SIS scope. The SIS code is in the following format, "XX-Y", where "XX" is the year the SIS scope was approved, and "Y" is a serial number within the given year.

## Load Project Tracking
Load Project Tracking Summary (by NYISO Zone and Requested MW)
MW By Status |  | A | B | C | D | E | F | G | H | I | J | K | NYCA
- | Withdrawn (not included in NYCA total) | 375 | 25 | 0 | 500 | 358 | 1104.38 | 296.5 | 0 | 0 | 0 | 420 | 3078.88
1 | Scoping Meeting Pending | 0 | 0 | 756 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 771
4 | SIS Pending | 1076 | 0 | 750 | 2135 | 1110 | 432 | 0 | 0 | 0 | 0 | 0 | 5503
5 | SIS In-Progress | 550 | 0 | 932 | 0 | 1799 | 0 | 150 | 1000 | 0 | 0 | 0 | 4431
6 | SIS Approved | 250 | 0 | 88 | 0 | 0 | 50 | 0 | 200 | 0 | 0 | 0 | 588
7 | FS Pending | 0 | 0 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110
9 | FS In-Progress | 140 | 0 | 576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 176.6 | 892.6
10 | Accepted Cost Allocation IA in Progress | 0 | 0 | 0 | 200 | 0 | 0 | 102.3 | 0 | 0 | 0 | 0 | 302.3
12 | Under Construction | 0 | 600 | 480 | 435 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1515
I/S | In-service | 300.2 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 360.2
| Total | 2016 | 600 | 3692 | 2770 | 2924 | 482 | 252.3 | 1200 | 0 | 0 | 176.6 | 14473.1
MW By End-Use |  | A | B | C | D | E | F | G | H | I | J | K | NYCA
DAT | Data Center (general) | 940 | 600 | 1458 | 320 | 750 | 180 | 252.3 | 1200 | 0 | 0 | 176.6 | 5876.9
DAT-AI | AI Datacenter | 1076 | 0 | 162 | 1935 | 2093 | 0 | 0 | 0 | 0 | 0 | 0 | 5266
DAT-CM | Cryptocurrency mining | 0 | 0 | 110 | 635 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 745
M | Manufacturing (general) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
M-CH | Microchip fabrication | 0 | 0 | 1056 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1056
M-CG | Consumable Goods | 0 | 0 | 0 | 0 | 66 | 40 | 0 | 0 | 0 | 0 | 0 | 106
M-IN | Industrial Goods | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 50
RD | Research and Development | 0 | 0 | 250 | 0 | 0 | 212 | 0 | 0 | 0 | 0 | 0 | 462
HP | Hydrogen Production | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
O | Other | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50
| Total | 2016 | 600 | 3086 | 2890 | 2909 | 482 | 252.3 | 1200 | 0 | 0 | 176.6 | 13611.9
Note total excludes withdrawn and in-service load projects
MW By IR Submission Date |  | A | B | C | D | E | F | G | H | I | J | K | NYCA | Running Total
44196 | 2020 and earlier | 0 | 300 | 110 | 435 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 845 | 845
44561 | 2021 | 0 | 0 | 0 | 320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 320 | 1165
44926 | 2022 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300 | 1465
45291 | 2023 | 0 | 0 | 1056 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 1106 | 2571
45657 | 2024 | 390 | 0 | 288 | 0 | 0 | 0 | 102.3 | 200 | 0 | 0 | 176.6 | 1156.9 | 3727.9
46022 | 2025 | 1626 | 0 | 732 | 2135 | 2909 | 372 | 0 | 1000 | 0 | 0 | 0 | 8774 | 12501.9
46387 | 2026 | 0 | 0 | 1506 | 0 | 15 | 60 | 150 | 0 | 0 | 0 | 0 | 1731 | 14232.9
| Total | 2016 | 600 | 3692 | 2890 | 2924 | 482 | 252.3 | 1200 | 0 | 0 | 176.6 | 14232.9
*Note total excludes withdrawn and in-service load projects